## Sheet1
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Test Data | Pre-Condition | Post-Condition | Expected Result | Actual Result | Status
TS-001 | Read Traffic Data From File | TC-001 | Verify the import Traffic Data Functionality regarding compatible files. | 1. Access Database with valid account. 2. Click import button compatible excel file into the GUI. | ValidAccount1 Password123! SampleFileComp.xlsx | 1. The user is logged in to the database. 2. The user must have a good connection to the internet. | Data is imported successfully into the GUI. | The data is successfully imported into the GUI for the user to view.
TS-001 | Read Traffic Data From File | TC-002 | Verify the import Traffic Data Functionality regarding incompatible files. | 1. Access Database with valid account. 2. Click import button on incompatible file into the GUI. | ValidAccount1 Password123! SampleFileIncomp.xlsx | 1. The user is logged in to the database. 2. The user must have a good connection to the internet. | The user is alerted that the file type is incompatible and therefore must select a comptabile file. | Error messages displays file is incompatible and asks user to import a compatible file.
TS-002 | View Traffic Data | TC-003 | Verify that the Dashboard containing All Traffic Data is up to date. | 1. Access Database with valid account. 2. Click on the option to view the Dashboard 1. | validAccount2 Password123! | 1. The user is logged in to the database. 2. The user must have a good connection to the internet. | The user is able to view an up to date Dashboard that contains All Traffic Data. | All the Traffic Data is shown to the user in the GUI.
TS-002 | View Traffic Data | TC-004 | Verify that the Dashboard containing Vehicle Specific Data is up to date. | 1. Access Database with valid account. 2. Click on the option to view the Dashboard 2. | validAccount2 Password123! | 1. User is logged into the database. 2. User has good internet connection. | The user will see an up to date Dashboard that contains all Vehicle Specific Data. | All the Vehicle Specific Data is shown to the User in the GUI.
TS-002 | View Traffic Data | TC-005 | Verify that the Dashboard containing Street Specific Data is up to date. | 1. Access Database with valid account. 2. Click on the option to view the Dashboard 3. | validAccount2 Password123! | 1. The user is logged in to the database. 2. The user must have a good connection to the internet. | The user will see an up to date Dashboard that contains all Street Specific Data. | All the Street Specific Data is shown to the User in the GUI.
TS-002 | View Traffic Data | TC-006 | Verify that the Dashboard containing County Specific Data is up to date. | 1. Access Database with valid account. 2. Click on the option to view the Dashboard 4. | validAccount2 Password123! | 1. The user must have good internet connection. 2. The user is logged into the database. | The user will see an up to date Dashboard that contains all County Specific Data. | All the County Specific Data is shown to the User in the GUI.
TS-002 | View Traffic Data | TC-007 | Verify that the dashboard filters are functioning correctly. | 1. Access Database with valid account. 2. Click on the option to view one of the Dashboards. 3. Click on Dashboard Filter. | validAccount2 Password123! | 1. The user must have good internet connection. 2. The user is logged into the database. | The user will see a Dashboard that may have been modified from it's original state due to the Dashboard filters. | A modified version of the selected Dashboard is shown reflecting the Filter changes.
TS-003 | Register | TC-008 | Verify Register functionality with valid Username (within requirements) and valid Password that have not yet been used by an account. | 1. Open GUI 2. Enter valid Username 3. Enter valid Password 4. Click Register button | NewValidAcc1 NewPass123! | 1. The user must have a good connection to the internet. 2. The user must be authorised to access the GUI before registering. | User has registered and is able to view database. | The user is now able to view the database after registering.
TS-003 | Register | TC-009 | Verify Register functionality with a valid Username (Within requirements) and valid Password that have already been registered. | 1. Open GUI 2. Enter valid Username of prexisting user. 3. Enter valid Password or password of prexisting user. 4. Click Register button | NewValidAcc1 NewPass123! (Note: We already registered with this user in the test case above so this suit the Test Case Description) | 1. The user must have a good connection to the internet. 2. The user must be authorised to access the GUI before registering. | Error message stating account already exists with selected Username. | Error messages tells the user that the Username they entered already exists to an account within the database. The user is able to re-enter log in details or sign up details.
TS-003 | Register | TC-010 | Verify Register functionality with valid Username and invalid Password. (Username that follows Username requirements and a password that does not follow password requirements.) | 1. Open GUI 2. Enter valid Username 3. Enter invalid Password 4. Click Register button | NewUser25 abc1! | 1. The user must have a good connection to the internet. 2. The user must be authorised to access the GUI before registering. | Error message stating Username or Password is incorrect. | Error message displays stating that the Username or Password is incorrect.
TS-003 | Register | TC-011 | Verify Register functionality with an Invalid Username and Invalid Password (Username and Password that do not follow requirements.) | 1. Open GUI 2. Enter invalid Username 3. Enter invalid Password 4. Click Register button. | /!£*& wes | 1. The user must have a good connection to the internet. 2. The user must be authorised to access the GUI before registering. | Error message stating Username or Password is incorrect. | Error message displays stating that the Username or Password is incorrect.
TS-004 | Login | TC-012 | Verify the log in functionality with a valid Username and password. | 1. Open GUI 2. Enter valid Username 3. Enter valid Password 4. Click Login button | NewValidAcc1 NewPass123! | 1. The user must have a good connection to the internet. 2. The user must be authorised to access the GUI before logging in. | User is able to view the data base using their account. | User is taken to Dashboard 1 (All Traffic Data dashboard).
TS-004 | Login | TC-013 | Verify the log in functionality with an invalid username and valid password (Password that follows password requirements). | 1. Open GUI 2. Enter Invalid Username 3. Enter valid Password 4. Click Login button | /!£*& NewPass123! | 1. The user must have a good connection to the internet. 2. The user must be authorised to access the GUI before logging in. | Error message stating Username or Password is incorrect. | Error message displays stating that the Username or Password is incorrect.
TS-004 | Login | TC-014 | Verify the log in functionality with an username and password that do not follow the username/password requirements or do not exist in the database. | 1. Open GUI 2. Enter invalid Username 3. Enter invalid Password 4. Click Login button | []##~ wakawaka | 1. The user must have a good connection to the internet. 2. The user must be authorised to access the GUI before logging in. | Error message stating Username or Password is incorrect. | Error message displays stating that the Username or Password is incorrect.
TS-005 | Logout | TC-015 | Verify the log out functionality. | 1. Access Database with valid account. 2. Click Logout button. | LogoutVal Logout123! | 1. The user must have a good connection to the internet. 2. The user must log in with a valid account. | Message displays stating user has successfully logged out. User is taken to log in screen. | Message displays stating user has successfully logged out. User is taken to log in screen.
TS-006 | Store Log Activity (Log In) | TC-016 | Verify if log is created when user logs in. | 1. Open GUI 2. Enter valid Username. 3. Enter valid Password. | LoginActAcc LoginActivity456? | 1. The user must have a good connection to the internet. 2. The user must be logged in with a valid account. | The user is able to view the database. The log in time has been stored into a separate log database. | The user is able to view the database. The log in time has been stored into the log database.
TS-007 | Store Log Activity (Log Out) | TC-017 | Verify if log is created when user logs out. | 1. Access Database with valid account. 2. Click Logout button. | LogoutActAcc <123Logout | 1. The user must have a good connection to the internet. 2. The user must | The user is able to exit the database. The log out time has been stored into a separate log activity database. | The user is able to exit the database. The log out time has been stored into the log database.
TS-008 | View Log Activity | TC-018 | Verify if admins are able to view the Log activity. | 1. Open GUI 2. Input valid Admin account Username and password. 3. Click Admin Panel. | AdminOne AdminPass789! | 1. The admin must have good connection to the internet. 2. Only admin accounts can view log activity. | The admin can view log activity information related to different users. The admin can choose a different option in the GUI or exit the GUI. | The admin is able to view all log activity related to users. The admin can also select different GUI features or exit the GUI if they want.
TS-009 | Administrate User Data | TC-019 | Verify if an admin can change user permissions. | 1. Open GUI 2. Input valid Admin account Username and password. 3. Click on Admin Panel. 4. Choose user to modify permissions. 5. Click Edit Button. 6. Click Admin button. 7. Click Save. | AdminTwo Ministrate1* | 1. The admin must have good connection to the internet. 2. Only admin accounts can modify permissions. | The admin is able to continue the permission change process on other users. A message will confirm the user had their permissions changed. The user now has access to admin controls. | Message confirms user selected has their permissions changed.
TS-009 | Administrate User Data | TC-020 | Verify if an admin can remove users from the database. | 1. Open GUI 2. Input valid Admin account Username and password. 3. Click on Admin Panel. 4. Choose user to be deleted. 5. Click Delete Button. 6. Click Admin button. 7. Click Save. | Admin20CharactersAccount SuperLongPassword9000! | 1. The admin must have good connection to the internet. 2. Only admin accounts can delete users. | The admin is able to continue the deletion process on other users. The user who attempts to log in to the GUI will be notified that their account details are invalid. | Message confirms user selected has been deleted and attempting to look for the user will not show anything.
TS-009 | Administrate User Data | TC-021 | Verify if an admin can edit a User's username. | 1. Open GUI 2. Input valid Admin account username and password. 3. Select Admin Panel. 4. Select Edit User. 5. Input Username of user to have their Username changed in top Username box. 6. Input new Username for current user in bottom Username box. 7. Select Save. | Admin20CharactersAccount SuperLongPassword9000! ChangeMe1 ChangedGuy1 | 1. The admin must have good connection to the internet. 2. Only admin accounts can modify User details. | The admin is able to continue the User modification process on other users. The user who attempts to log in using their old Username into the GUI will be notified that their account details are invalid. | Message confirms user selected has been modified successfully.
TS-009 | Administrate User Data | TC-022 | Verify if an admin can edit a User's password. | 1. Open GUI 2. Input valid Admin account username and password. 3. Select Admin Panel. 4. Select Edit User. 5. Input Username of user to have their Password changed in top Username box. 6. Input current Password of user to have their Password changed in top Password box. 6. Input new Password for current user in bottom Password box. 7. Select Save. | Admin20CharactersAccount SuperLongPassword9000! GonnaBeModi2 NotModiYet23! ModifiedPass123! | 1. The admin must have good connection to the internet. 2. Only admin accounts can modify User details. | The admin is able to continue the User modification process on other users. The user who attempts to log in using their old Password into the GUI will be notified that their account details are invalid. | Message confirms user selected has been modified successfully.
TS-009 | Administrate User Data | TC-023 | Verify that the Admin cannot change a User's username to a pre-existing username. | 1. Open GUI 2. Input valid Admin account username and password. 3. Select Admin Panel. 4. Select Edit User. 5. Input Username of user to have their Username changed in top Username box. 6. Input pre-existing Username for current user in bottom Username box. 7. Select Save. | Admin20CharactersAccount SuperLongPassword9000! AnExistingUser1 AnotherUser2 | 1. The admin must have good connection to the internet. 2. Only admin accounts can modify User details. | A message will be displayed alerting the User that the Username already exists and cannot be changed. The admin is able to continue the User modification process on other users. The User can log into their account as usual. | Message states that the requested Username is invalid.
TS-009 | Administrate User Data | TC-024 | Verify that the Admin cannot change a User's username to a Username that doesn't follow Username requirements. | 1. Open GUI 2. Input valid Admin account username and password. 3. Select Admin Panel. 4. Select Edit User. 5. Input Username of user to have their Username changed in top Username box. 6. Input invalid Username in bottom Username box. 7. Select Save. | Admin20CharactersAccount SuperLongPassword9000! AllowedUser1 !? | 1. The admin must have good connection to the internet. 2. Only admin accounts can modify User details. | A message will be displayed alerting the User that the requested Username is invalid. The admin is able to continue the User modification process on other users. The User can log into their account as usual. | Message states that the requested Username is invalid.
TS-009 | Administrate User Data | TC-025 | Verify that the Admin cannot change a User's Password to a Password that doesn't follow Password requirements. | 1. Open GUI 2. Input valid Admin account username and password. 3. Select Admin Panel. 4. Select Edit User. 5. Input Username of user to have their Password changed in top Username box. 6. Input current Password of user to have their Password changed in top Password box. 6. Input invalid Password for current user in the bottom Password box. 7. Select Save. | Admin20CharactersAccount SuperLongPassword9000! HelloMan24 ChangeEqualsNo890? /92ab | 1. The admin must have good connection to the internet. 2. Only admin accounts can modify User details. | A message will be displayed stating that the requested Password is invalid. The admin is able to continue the User modification process on other users. The user can still access their account using their current details. | Message states that the requested Password is invalid.
TS-009 | Administrate User Data | TC-026 | Verify that the Admin cannot change both the Username and Password which do not follow requirements at the same time. | 1. Open GUI 2. Input valid Admin account username and password. 3. Select Admin Panel. 4. Select Edit User. 5. Input Username of user to have their details changed in top Username box. 6. Input invalid username in the bottom Username box. 7. Input current Password of user to have their Password changed in top Password box. 8. Input invalid Password for current user in the bottom Password box. 7. Select Save. | Admin20CharactersAccount SuperLongPassword9000! RegularUser1 // ChangeEqualsNo890? /92ab | 1. The admin must have good connection to the internet. 2. Only admin accounts can modify User details. | A message will be displayed stating that the requested Username and Password is invalid. The admin is able to continue the User modification process on other users. The user can still access their account using their current details. | Message states that the requested Username and Password is invalid.
TS-009 | Administrate User Data | TC-027 | Verify that the Admin cannot change a User's username to a pre-existing username and the User's Password which do not follow requirements at the same time. | 1. Open GUI 2. Input valid Admin account username and password. 3. Select Admin Panel. 4. Select Edit User. 5. Input Username of user to have their details changed in top Username box. 6. Input Pre-existing username in the bottom Username box. 7. Input current Password of user to have their Password changed in top Password box. 8. Input invalid Password for current user in the bottom Password box. 7. Select Save. | Admin20CharactersAccount SuperLongPassword9000! UserDunk900 UserWhoExists10 ChangeEqualsNo890? /92ab | 1. The admin must have good connection to the internet. 2. Only admin accounts can modify User details. | A message will be displayed stating that the requested Username and Password is invalid. The admin is able to continue the User modification process on other users. The user can still access their account using their current details. | Message states that the requested Username and Password is invalid.